## Sheet1
www.goodoldmanoj.com
Burn down chart
Project | Story | Task | Start | Day 12 | Day 11 | Day 10 | Day 9 | Day 8 | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1
Android | Pengenalan Android | Apa itu Android ? | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Android | Pengenalan Android | Sedikit Sejarah Android | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Android | Pengenalan Android | Jelaskan ICS | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0
Android | Pengenalan Android | Jelaskan JB | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0
Android | Pengenalan Android | Jelaskan Kitkat | 4 | 2 | 2 | 2 | 2 | 0 | 0 | 0
Android | Trik Android | Rooting | 6 | 6 | 6 | 4 | 2 | 0 | 0 | 0
Android | Trik Android | Custom Roms | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
Android | Trik Android | Flashing | 6 | 6 | 6 | 3 | 3 | 0 | 0 | 0
Android | Masalah di android | BootLoop | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0
Android | Masalah di android | Masalah Umum | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0
Android | Benchmark | Apa itu Benchmark | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Android | Benchmark | Kegunaan Benchmark | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Android | Benchmark | Benchmark Apps | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0
Android | Beberapa Aplikasi Android yang kami sarankan | 5 Aplikasi Games yang kami sarankan | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0
Android | Beberapa Aplikasi Android yang kami sarankan | 5 Aplikasi Sosial Media yang kami sarankan | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0
Android | Beberapa Aplikasi Android yang kami sarankan | 5 Aplikasi Utility yang kami sarankan | 9 | 9 | 9 | 9 | 9 | 9 | 0 | 0
Android | Re-Checking, Re-Correct, Re-Designing | Meringkas/menghapus topik Pengenalan Android | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Android | Re-Checking, Re-Correct, Re-Designing | Meringkas/menghapus topik Trik Android
Android | Re-Checking, Re-Correct, Re-Designing | Meringkas/menghapus topik Masalah di Android | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Android | Re-Checking, Re-Correct, Re-Designing | Meringkas/menghapus topik Benchmark | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Android | Re-Checking, Re-Correct, Re-Designing | Meringkas/menghapus topik Aplikasi Android yang Disarankan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Android | Re-Checking, Re-Correct, Re-Designing | Meringkas/menghapus topik Android Google Play | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Android | Jenis-jenis Layar | Jenis-jenis Layar | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Android | Tips Memilih Layar | Tips Memilih Layar | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Android
Android
Ideal - Remaining efforts in uninterrupted working hours |  |  | 77 | 70.5833 | 64.1667 | 57.75 | 51.3333 | 44.9167 | 38.5 | 32.0833 | 25.6667 | 19.25 | 12.8333 | 6.4167 | 0
Actual - Remaining efforts in uninterrupted working hours |  |  | 77 | 71 | 67 | 58 | 53 | 46 | 3 | 3
Note on H5: goodoldmanoj.com: Remaining effort as of that day to complete the task. NOT last day effort - hours worked. So this can go up if new challenges got uncovered
Note on I5: Remaining effort as of that day to complete the task.It's NOT last day effort - hours worked. So this can go up if new challenges got uncovered