## Sheet1
www.goodoldmanoj.com
Burn down chart
Project | Story | Task | Start | Day 10 | Day 9 | Day 8 | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1
Android | Story 1 | Task 1.1 | 8 | 4 | 0 | 0 | 0 | 0
Android | Story 1 | Task 1.2 | 6 | 2 | 3 | 5 | 2 | 0
Android | Story 1 | Task 1.3 | 5 | 5 | 3 | 2 | 2 | 0
Android | Story 2 | Task 2.1 | 8 | 8 | 8 | 8 | 7 | 3
Android | Story 2 | Task 2.2 | 8 | 8 | 8 | 8 | 8 | 7
Android | Story 3 | Task 3.1 | 9 | 9 | 9 | 9 | 9 | 9
Android | Story 3 | Task 3.2 | 5 | 5 | 5 | 5 | 5 | 5
Android | Story 3 | Task 3.3 | 7 | 7 | 7 | 7 | 7 | 7
Android | Story 3 | Task 3.4 | 3 | 3 | 3 | 3 | 3 | 3
Android | Story 4 | Task 4.1 | 8 | 8 | 8 | 8 | 8 | 8
Android | Story 4 | Task 4.2 | 6 | 6 | 6 | 6 | 6 | 6
Android | Story 4 | Task 4.3 | 8 | 8 | 8 | 8 | 8 | 8
Android | Story 4 | Task 4.4 | 9 | 9 | 9 | 9 | 9 | 9
Ideal - Remaining efforts in uninterrupted working hours |  |  | 90 | 81 | 72 | 63 | 54 | 45 | 36 | 27 | 18 | 9 | 0
Actual - Remaining efforts in uninterrupted working hours |  |  | 90 | 82 | 77 | 78 | 74 | 65
Note on F5: goodoldmanoj.com: Remaining effort as of that day to complete the task. NOT last day effort - hours worked. So this can go up if new challenges got uncovered
Note on G5: Remaining effort as of that day to complete the task.It's NOT last day effort - hours worked. So this can go up if new challenges got uncovered