## Sheet1
www.goodoldmanoj.com
Burn down chart
Project | Story | Task | Start | Day 10 | Day 9 | Day 8 | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1
Android | Pengenalan Android | Apa itut Android ? | 2 | 4 | 0 | 0 | 0 | 0
Android | Pengenalan Android | Sedikit Sejarah Android | 2 | 2 | 3 | 5 | 2 | 0
Android | Pengenalan Android | Jelaskan ICS | 2
Android | Pengenalan Android | Jelaskan JB | 2
Android | Pengenalan Android | Jelaskan Kitkat | 2 | 5 | 3 | 2 | 2 | 0
Android | Story 2 | Task 2.1 | 8 | 8 | 8 | 8 | 7 | 3
Android | Story 2 | Task 2.2 | 8 | 8 | 8 | 8 | 8 | 7
Android | Story 3 | Task 3.1 | 9 | 9 | 9 | 9 | 9 | 9
Android | Story 3 | Task 3.2 | 5 | 5 | 5 | 5 | 5 | 5
Android | Story 3 | Task 3.3 | 7 | 7 | 7 | 7 | 7 | 7
Android | Story 3 | Task 3.4 | 3 | 3 | 3 | 3 | 3 | 3
Android | Story 4 | Task 4.1 | 8 | 8 | 8 | 8 | 8 | 8
Android | Story 4 | Task 4.2 | 6 | 6 | 6 | 6 | 6 | 6
Android | Story 4 | Task 4.3 | 8 | 8 | 8 | 8 | 8 | 8
Android | Story 4 | Task 4.4 | 9 | 9 | 9 | 9 | 9 | 9
Ideal - Remaining efforts in uninterrupted working hours |  |  | 81 | 72.9 | 64.8 | 56.7 | 48.6 | 40.5 | 32.4 | 24.3 | 16.2 | 8.1 | 0
Actual - Remaining efforts in uninterrupted working hours |  |  | 81 | 82 | 77 | 78 | 74 | 65
Note on F5: goodoldmanoj.com: Remaining effort as of that day to complete the task. NOT last day effort - hours worked. So this can go up if new challenges got uncovered
Note on G5: Remaining effort as of that day to complete the task.It's NOT last day effort - hours worked. So this can go up if new challenges got uncovered