## Sheet1
www.goodoldmanoj.com
Burn down chart
Project | Story | Task | Start | Day 12 | Day 11 | Day 10 | Day 9 | Day 8 | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1
Android | Pengenalan Android | Apa itu Android ? | 2 | 2 | 0 | 0 | 0 | 0
Android | Pengenalan Android | Sedikit Sejarah Android | 2 | 2 | 0 | 0 | 0 | 0
Android | Pengenalan Android | Jelaskan ICS | 4 | 2 | 2 | 0 | 0 | 0
Android | Pengenalan Android | Jelaskan JB | 4 | 2 | 2 | 0 | 0 | 0
Android | Pengenalan Android | Jelaskan Kitkat | 4 | 2 | 2 | 2 | 2 | 0
Android | Trik Android | Rooting | 6 | 6 | 6 | 4 | 2 | 0
Android | Trik Android | Custom Roms | 3 | 3 | 3 | 3 | 0 | 0
Android | Trik Android | Flashing | 6 | 6 | 6 | 3 | 3 | 0
Android | Masalah di android | BootLoop | 6 | 6 | 6 | 6 | 6 | 6
Android | Masalah di android | Masalah Umum | 4 | 4 | 4 | 4 | 4 | 4
Android | Benchmark | Apa itu Benchmark | 1 | 1 | 1 | 1 | 1 | 1
Android | Benchmark | Kegunaan Benchmark | 1 | 1 | 1 | 1 | 1 | 1
Android | Benchmark | Benchmark Apps | 10 | 10 | 10 | 10 | 10 | 10
Android | Beberapa Aplikasi Android yang kami sarankan | 5 Aplikasi Games yang kami sarankan | 8 | 8 | 8 | 8 | 8 | 8
Android | Beberapa Aplikasi Android yang kami sarankan | Task 4.4 | 9 | 9 | 9 | 9 | 9 | 9
Ideal - Remaining efforts in uninterrupted working hours |  |  | 70 | 64.1667 | 58.3333 | 52.5 | 46.6667 | 40.8333 | 35 | 29.1667 | 23.3333 | 17.5 | 11.6667 | 5.8333 | 0
Actual - Remaining efforts in uninterrupted working hours |  |  | 70 | 64 | 60 | 51 | 46 | 39
Note on H5: goodoldmanoj.com: Remaining effort as of that day to complete the task. NOT last day effort - hours worked. So this can go up if new challenges got uncovered
Note on I5: Remaining effort as of that day to complete the task.It's NOT last day effort - hours worked. So this can go up if new challenges got uncovered