## Sheet1
www.goodoldmanoj.com
Burn down chart
Project | Story | Task | Start | Day 12 | Day 11 | Day 10 | Day 9 | Day 8 | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1
Android | Pengenalan Android | Apa itu Android ? | 2 | 2 | 0 | 0 | 0 | 0
Android | Pengenalan Android | Sedikit Sejarah Android | 2 | 2 | 0 | 0 | 0 | 0
Android | Pengenalan Android | Jelaskan ICS | 4 | 2 | 2 | 0 | 0 | 0
Android | Pengenalan Android | Jelaskan JB | 4 | 2 | 2 | 0 | 0 | 0
Android | Pengenalan Android | Jelaskan Kitkat | 4 | 2 | 2 | 2 | 2 | 0
Android | Trik Android | Rooting | 6 | 6 | 6 | 4 | 2 | 0
Android | Trik Android | Custom Roms | 3 | 3 | 3 | 3 | 0 | 0
Android | Trik Android | Flashing | 6 | 6 | 6 | 3 | 3 | 0
Android | Masalah di android | BootLoop | 4 | 4 | 4 | 4 | 4 | 4
Android | Masalah di android | Masalah Umum | 7 | 7 | 7 | 7 | 7 | 7
Android | Benchmark | Apa itu Benchmark | 3 | 3 | 3 | 3 | 3 | 3
Android | Benchmark | Benchmark Apps | 6 | 6 | 6 | 6 | 6 | 6
Android | Benchmark | Re-design tampilan | 10 | 10 | 10 | 10 | 10 | 10
Android | Story 4 | Task 4.3 | 8 | 8 | 8 | 8 | 8 | 8
Android | Story 4 | Task 4.4 | 9 | 9 | 9 | 9 | 9 | 9
Ideal - Remaining efforts in uninterrupted working hours |  |  | 78 | 71.5 | 65 | 58.5 | 52 | 45.5 | 39 | 32.5 | 26 | 19.5 | 13 | 6.5 | 0
Actual - Remaining efforts in uninterrupted working hours |  |  | 78 | 59 | 54 | 47 | 0 | 0
Note on H5: goodoldmanoj.com: Remaining effort as of that day to complete the task. NOT last day effort - hours worked. So this can go up if new challenges got uncovered
Note on I5: Remaining effort as of that day to complete the task.It's NOT last day effort - hours worked. So this can go up if new challenges got uncovered